## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Positive | Customers were generally satisfied with the tablet ordering experience. | 72% rated the tablet experience as Good (40%) or Great (32%). | Proceed with the phased rollout while continuing to monitor customer satisfaction.
Customers | Positive | Waiter instructions were effective for most users. | 76% said the waiter explained how to use the tablet very well. | Continue staff training and standardize tablet demonstrations.
Customers | Improvement | Tablet navigation and ordering were not intuitive for everyone. | 22% found navigation difficult/slightly difficult, and 26% found ordering difficult/slightly difficult. | Improve the user interface, simplify navigation, and add an on-screen tutorial.
Customers | Improvement | Long table wait times affected the overall dining experience. | 54% waited more than 15 minutes for a table. | Optimize table management, reservations, and seating processes.
Customers | Improvement | Order accuracy needs improvement. | 28% reported receiving an incorrect order, including wrong items or missed substitutions. | Introduce kitchen order verification and improve communication between the tablet system and kitchen staff.
Customers | Positive | Checkout process was well received. | 82% agreed the checkout process was quick, easy, and secure. | Maintain the digital payment process while adding clearer support for cash payments.
Customers | Improvement | A few customers experienced technical issues with the tablets. | 12% reported issues such as screen freezing or glitches. | Resolve software bugs, improve tablet stability, and establish routine device maintenance.
Project Team | Positive | Customer engagement through the tablet was successful. | 78% signed up for the newsletter using the tablet. | Continue using the tablet for marketing campaigns and customer engagement initiatives.
Project Team | Improvement | Birthday Club enrollment was low. | Only 16% signed up for the Birthday Club. | Increase visibility of the Birthday Club and offer incentives (e.g., free dessert or discount) for joining.
Project Team | Went Well | Tablet installation and implementation were completed successfully. | All tablets were installed and functioning properly during the test launch. | Follow the same installation process for future restaurant rollouts.
Project Team | Needs Improvement | Table turn time did not improve as expected. | Despite tablet ordering, customers stayed at tables for about the same amount of time. | Analyze dining workflow, checkout, and seating process to reduce table turn time.
Project Team | Went Well | Customers adapted quickly to using the tablets and payments worked smoothly. | Guests learned the tablet system with minimal issues. | Continue customer guidance and maintain the digital payment process.
Project Team | Needs Improvement | Food order accuracy still requires improvement. | Some orders were sent back even though ticket flow improved. | Investigate causes of incorrect orders and improve kitchen verification processes.
Project Team | Went Well | Technical issues during POS integration were identified and resolved quickly. | Integration problems were fixed during testing without major delays. | Update the troubleshooting guide and process manual with the solutions.
Project Team | Needs Improvement | Tablet implementation took longer than planned because staff vacations were not considered. | Resource availability affected the implementation schedule. | Include employee availability and vacation planning in the project schedule.
Project Team | Needs Improvement | Back-of-house staff need additional preparation for higher order volumes. | Kitchen staff requested more readiness before full launch. | Provide operational scaling and capacity training before rollout.
Project Team | Needs Improvement | Limited understanding between front-of-house and back-of-house teams reduced collaboration. | Staff tended to blame each other when issues occurred. | Introduce cross-functional training and job-shadowing sessions to improve teamwork.