## Slide 1: Sauce & Spoon Tabletop Menu Tablet Pilot Project

## Slide 2: Summary
Objective
Conduct a pilot test of Sauce & Spoon’s tablet ordering system to evaluate customer experience
before a full rollout.
How the milestone was achieved
Conducted a live test with 50 customers.
Customers completed a full dining experience using the tablets.
Digital survey collected feedback after the meal.
Evaluated customer satisfaction, usability, checkout, technical performance and operational efficiency.
Outcome
The test launch successfully gathered customer feedback and identified strengths and improvement opportunities for the next rollout phase.

## Slide 3
Evaluation Goals
Assess overall customer satisfaction with the tablet ordering system.
Evaluate the ease of navigation, ordering, and payment.
Measure the effectiveness of staff guidance and tablet usability.
Determine the system's impact on service efficiency, order accuracy, and wait times.
Identify customer preferences, technical issues, and opportunities for future improvements.

## Slide 4
Findings
Chart: Satisfaction on Tablet
| 1 - Lacking/ Difficult | 2 - Mediocre/ Slightly Difficult | 3 - Neutral | 4 - Good/ Fairly Easy | 5 - Great/ Very Easy
Tablet Experience | 4 | 10 | 14 | 40 | 32
Tablet Navigation | 4 | 18 | 30 | 28 | 20
Easy to Order | 8 | 18 | 28 | 24 | 22
72% of customers rated their overall tablet experience as Good or Great (4 or 5 out of 5).
58% of customers rated the tablet navigation as Fairly Easy or Very Easy (4 or 5 out of 5).
46% of customers found it Fairly Easy or Very Easy to order directly from the tablet (4 or 5 out of 5).

## Slide 5
Next Steps
Supporting findings
  22% found ordering difficult or slightly difficult.
  24% felt waiter instructions were not sufficient.
  Several customers reported tablets freezing or being glitchy.
Recommendation
  Provide clearer waiter demonstrations.
  Add a brief on-screen tutorial.
  Improve tablet software stability before full deployment.
Expected Benefit
  Better user confidence
  Faster ordering
  Fewer support requests
  Higher customer satisfaction

## Slide 6
Next Steps
Supporting findings
  54% waited more than 15 minutes for a table.
  28% experienced incorrect food orders.
  30% preferred a mix of tablet ordering and waiter interaction.
  Comments requested the option to choose traditional waiter service.
Recommendation
  Reduce table wait times through improved scheduling.
  Strengthen kitchen order verification.
  Offer customers a choice between tablet-assisted and traditional waiter service.
Expected Benefit
  Improved customer satisfaction
  Higher order accuracy
  Greater flexibility for different customer preferences
  Better readiness for a successful full-scale rollout