## Slide 1
Stakeholder Analysis
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Omar Mubarak | Owner & CEO | High | Medium | Final decision-maker and project sponsor.
Deanna Coleman | Director of Operations | High | High | Project sponsor; oversees operations and supports execution.
Carter Ward | Executive Chef | Medium | High | Key influence for kitchen changes.
Gilly Tyson | General Manager (North) | Medium | High | Pilot North restaurant GM, provide feedback of the restaurant and training to employee.
Alex Schmidt | General Manager (Downtown) | Medium | High | Pilot North restaurant GM, provide feedback of the restaurant and training to employee.
Nia Willams | General Manager (Waterfront) | Low | Medium | Not part of pilot project, but involve in the future project expansion.
Zane Dutchman | Kitchen Manager (North) | Low | High | Overseas kitchen operations of North pilot restaurant.
Larissa Stein | Kitchen Manager (Downtown) | Low | High | Runs kitchen operations of Downtown pilot restaurant.

## Slide 2
Stakeholder Analysis
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Seydou Diallo | Restaurant Technology Consultant | Medium | High | Technical experts who are integrate technology with business needs.

## Slide 3
Keep satisfied (high priority)
Omar
Manage closely (high effort)
Deanna
Monitor (minimum effort)
Nia
Zane
Larissa
Show consideration
Carter
Gilly
Alex
Seydou
Power
high
low
med
high
low
Omar
Owner
Drag each stakeholder’s box to the appropriate place on the power-interest grid
Deanna
Director of Operations
Carter
Exec. Chef
Gilly
GM - North
Alex
GM - Downtown
Zane
Kitchen Manager - North
Larissa
Kitchen Manager - Downtown
Seydou
Restaurant Consultant
Interest
med
Nia
General Manager - Waterfront